## Weekly Plan
Quarter | Week | Task | Description | Estimated Time | Difficulty (1–5)
Q1 | Week 1 | Project Setup | Create GitHub repository, define README, initialize Python app structure | 6–8 hrs | 2
Q1 | Week 2 | Makefile & Requirements | Write Makefile with targets (install, test, lint); create requirements.txt | 4–6 hrs | 2
Q1 | Week 3 | Linting Setup | Integrate pylint, flake8, or similar; fix basic lint issues | 4–6 hrs | 2
Q1 | Week 4 | Unit Testing Setup | Add sample test cases using pytest; run locally | 6–8 hrs | 3
Q1 | Week 5 | GitHub Actions – CI | Create .github/workflows/ci.yml for lint, test, build automation | 6–10 hrs | 3
Q1 | Week 6 | Badge Integration | Add build status badges to README | 2 hrs | 1
Q1 | Week 7 | Azure Account Setup | Create Azure App Service, Service Principal, and Resource Group | 8–10 hrs | 4
Q1 | Week 8 | Azure Pipeline Setup | Create Azure Pipeline YAML for CD (deploy to staging) | 8–12 hrs | 4
Q1 | Week 9 | CI/CD Integration | Connect GitHub to Azure DevOps; ensure successful end-to-end build + deploy | 10–12 hrs | 4
Q1 | Week 10 | Environment Variables & Secrets | Add secrets management (GitHub Secrets, Azure Key Vault) | 6–8 hrs | 3
Q1 | Week 11 | Testing End-to-End Flow | Simulate code changes → trigger pipeline → deploy → validate app | 8–10 hrs | 4
Q1 | Week 12 | Documentation & Demo | Finalize README, pipeline diagram, and record demo | 4–6 hrs | 2
Q2 | Week 13 | Pipeline Optimization | Add job matrix (Python versions / OS) | 6–8 hrs | 3
Q2 | Week 14 | Environment-based Deployments | Create dev/staging/prod pipelines | 8–10 hrs | 4
Q2 | Week 15 | Quality Gates | Integrate code coverage (pytest-cov) and lint thresholds | 8 hrs | 3
Q2 | Week 16 | Notifications & Logs | Add Slack/email build notifications and artifact logs | 6–8 hrs | 3
Q2 | Week 17 | Revision-wise Troubleshooting Implementation | Capture commit SHA, author, and build metadata in CI/CD logs; automate detection of commit causing failure | 10–12 hrs | 4
Q2 | Week 18 | Revision-wise Troubleshooting Validation | Run test scenario with multiple commits → simulate failure → trace offending commit and rollback | 8–10 hrs | 4
Q2 | Week 19 | Pipeline Cleanup & Optimization | Refactor YAML, add caching, improve runtime | 6–8 hrs | 3
Q2 | Week 20 | Optimization Review & Documentation | Update pipeline diagrams and write troubleshooting guide | 4–6 hrs | 2

## Quarterly Plan
Quarter | Focus Areas | Key Activities | Deliverables
Q1 | Core CI/CD Setup | Build GitHub repo, Makefile, linting, testing, automation; integrate with GitHub Actions and Azure Pipelines | Working CI/CD pipeline with deploys to Azure App Service
Q2 | CI/CD Optimization | Add automated testing matrix, environment-based deployments, code coverage, and revision-wise troubleshooting | Optimized pipelines with automated commit traceability
Q3 | Monitoring & Security | Add monitoring hooks (App Insights, Azure Monitor), enable secrets management & security scanning, rollback automation | Secure and observable delivery pipeline
Q4 | Scaling & Continuous Improvement | Integrate Docker, migrate to Terraform IaC, automate release notes and change tracking | Fully automated and scalable CI/CD ecosystem

## Difficulty Estimates
Task | Estimated Time | Difficulty (1–5) | Comments
Create GitHub Repo & App Structure | 6–8 hrs | 2 | Basic repo setup
Write Makefile and requirements.txt | 4–6 hrs | 2 | Simple automation
Setup Linting (pylint/flake8) | 4–6 hrs | 2 | Low complexity
Add Unit Tests (pytest) | 6–8 hrs | 3 | Some debugging needed
Configure GitHub Actions (CI) | 8–10 hrs | 3 | YAML + workflow syntax
Setup Azure Environment | 8–10 hrs | 4 | Requires Azure familiarity
Create Azure Pipeline (CD) | 8–12 hrs | 4 | Multi-step YAML + deploy logic
Integrate CI/CD (GitHub + Azure) | 10–12 hrs | 4 | Troubleshooting integration
Add Secrets Management | 6–8 hrs | 3 | Secure configuration
End-to-End Validation | 8–10 hrs | 4 | Final verification
Documentation & Demo | 4–6 hrs | 2 | Report + screenshots
Implement Revision-wise Troubleshooting | 10–12 hrs | 4 | Capture commit metadata, map failures to commits, enable rollback
Validate Revision-wise Troubleshooting | 8–10 hrs | 4 | Simulate multi-commit pipeline failure, confirm detection accuracy

## Yearly Summary
Quarter | Focus | Key Deliverables
Q1 | Core CI/CD Setup | GitHub repo, Makefile, lint, test, GitHub Actions, Azure pipeline
Q2 | Optimization | Test matrix, environment deployments, coverage, and revision-wise troubleshooting
Q3 | Monitoring & Security | Monitoring, security scanning, and rollback automation
Q4 | Scaling & Improvements | Containerization, IaC (Terraform), and release automation